## Task Breakdown
| Category | Task | Est. Hours | Priority | Notes / Dependencies | Scope
1 | Channel Consolidation | Remove routing logic for rising, popular, approved list, and trending channels | 1 | High | Touches channel ID configs and .env variables | In Scope
2 | Channel Consolidation | Retain only 'game requests' and 'new submissions' channels | 1 | High | Keep archive channel with 14-day auto-move logic intact | In Scope
3 | Channel Consolidation | Update all environment variable references and Discord server channel setup | 1 | High | Coordinate with Leon to archive/delete old channels on server | In Scope
4 | Sorting & Filtering | Implement periodic bot function to re-order posts by vote count | 2 | Medium | Discord API does not allow bots to reorder threads/forum posts — replaced by /top command | Out of Scope
5 | Sorting & Filtering | Create pinned message explaining how to filter by game name | 0.5 | Low | Simple channel pin — no code required | In Scope
6 | Sorting & Filtering | Add /top slash command posting a ranked list of games on demand | 1.5 | Medium | Optional but improves UX significantly | In Scope
7 | Single-Step Submission | Redesign modal to fit all fields (language, title, link, familiarity, pay) within Discord's 5-field limit | 2 | High | Language dropdown cannot go inside a Discord modal; workaround: text input or pre-modal select | In Scope
8 | Single-Step Submission | Remove 'continue to step 2' button and its interaction handler | 0.5 | High | Clean up dead code paths | In Scope
9 | Single-Step Submission | End-to-end testing of the new single-step flow | 0.5 | High | Test on private channel before go-live | In Scope
10 | Reset Command | Add admin-only /reset slash command | 1 | High | Restrict to admin role; confirm prompt before executing | In Scope
11 | Reset Command | Clear vote data from bot internal state on reset | 0.5 | High | Ensure all in-memory and persisted state is wiped | In Scope
12 | Reset Command | Wipe / create fresh tab in the connected Google Sheet on reset | 0.5 | High | Preserve sheet structure; only clear data rows | In Scope
13 | Auto Data Export | Add vote threshold check on every vote event | 0.5 | Medium | Trigger when game first crosses 100 votes | In Scope
14 | Auto Data Export | Generate clean game summary (title, link, language, vote breakdown, pay stats) | 1.5 | Medium | Format for presentation to game developers | In Scope
15 | Auto Data Export | Post summary to private admin channel or new Google Sheet tab | 1 | Medium | Confirm destination with Leon — Google Sheets preferred | In Scope
16 | Bug Fixes & QA | Diagnose and fix rising/popular threshold logic not triggering correctly | 1.5 | High | e.g. Hollow Knight not moving to rising despite sufficient votes | In Scope
17 | Bug Fixes & QA | General code review and cleanup of removed channel logic | 1 | Medium | Remove dead env vars, orphan handlers, and stale comments | In Scope
18 | Bug Fixes & QA | Full end-to-end QA on private Discord channel | 1.5 | High | Daniel to be added to Leon's server for testing | In Scope
19 | Bug Fixes & QA | Deploy updated bot to Render and confirm stable operation | 0.5 | High | Verify bot stays online; check Render logs post-deploy | In Scope
|  | TOTAL ESTIMATED HOURS | 19.5
BUFFER & CONTINGENCY
B1 | Environment Setup & Onboarding | Initial codebase review, local setup, Render access, Google Sheets auth, Discord dev portal config | 3 | High | One-time cost; needed before any dev work begins | In Scope
B2 | Integration Testing | Test all modified flows together (submission → vote → export → reset) in a controlled server environment | 2 | High | Requires Daniel to be added to Leon's Discord server | In Scope
B3 | Bug Fix Buffer | Contingency for unexpected issues discovered during QA or integration testing | 2 | Medium | Standard 15–20% buffer on a project of this size | In Scope
B4 | Deployment & Handover | Final deploy to Render, smoke test on live server, handover notes to Leon | 1 | High | Includes documenting any new env vars or slash commands added | In Scope
|  | BUFFER SUBTOTAL | 8
GRAND TOTAL (Tasks + Buffer) |  |  | 27.5